## ProjectRiskRegister
Project Risk Register
Project Details
Project Name: |  |  |  | PR01 City Green Plan
Location: |  |  |  | City Park,
Project Manager / Responsible Officer: |  |  |  | Joe Smith - Manager
Delivery Manager / Design Manager:
Client Unit: |  |  |  | City Services
Risk Details | [8 empty] | Control Details |  |  |  |  | Residual Risk Rating |  |  | Treatment Action Details
Risk Code | Title | Sub Event | Phase | Causes | Consequences | P10 Projection | P50 Projection | P90 Projection | Control Strategy |  | Controls | Control Effectiveness | Control Owner | Likelihood | Consequences | Risk Rating | Action Strategy | Treatment Actions | Action Owner | Action Status | % Complete
R-1 | Failure to deliver the City project | Project Risk Register | Ongoing Program | Ongoing theft and anti-social activities at the site | The City would be unable to meet its commitments to partner with community stakeholders on the City project |  |  |  |  | Business Plan review - in progress. Environmental Management Plan; complete October 2022 Resource development of schools Planning irrigation installation in plant nursery School volunteering programs held City Education schedule developed including free talks, hands-on sessions and workshops - ongoing Work with site auditor on next steps for environmental site suitability - in progress Launch of the City Community Hub Master Plan prepared - completed Employ a project manager to deliver the project - completed Prepare a business plan for Council approval - completed Preparation of a Project Plan for the delivery of the City Project - in progress Preparation of a City Business Plan to be approved by Executive and Council - completed City employing a project manager to progress the business plan and master plan implementation - completed Building the PowerHouse Museum Establishment of a City Advisory Group |  |  |  | Possible | Moderate - Service Delivery | High | Onsite city programs recommenced in late April Stopping in August, and recommencing in December Programs re-paused in June due to lockdown Plans are updated inline with changing requirements Selection of education offer turning into webinars for online delivery Exploring opportunities for online activities / digital engagement Follow steps recommended by City engaged site auditor to ensure that Park site is suitable for proposed use as City Project - in progress Involve representatives from the City's Risk, Legal and Health teams in discussions on environmental considerations - ongoing Involve community in City volunteer sessions - ongoing Provide CEO updates as appropriate - ongoing Develop a Communications Strategy and Brand as part of the project implementation - completed Continue to engage and develop community support for the City project through business plan review process - in progress
|  |  |  | Council, community or stakeholders not continuing to support the City | The community, sustainability and environmental educational capacity building goals of the project would be not be met, and the City's reputation would be negatively impacted
External risks related to WestConnex development
Drought and water restrictions
Business Plan concepts and modelling being outdated and not relevant to present community expectations and current market
Inadequate resourcing or funding for the project