## Risk Action Report
Atlantis Risk Action Report
Print Date: 26/09/2023
100%
Risk Title | Action Owner | Action Owner Position Title | Risk Action Title | Percentage Completed | Performance | Start Date | Original End Date | Revised End Date | Deviation (Months) | Duration (Months) | # of Extensions | Risk Owner Comments | ERC Comments
Business Disruption | Sharon Lang | Program Director | Complete business impact analysis | 40% | On Track | 2021-01-27 | 2021-12-27 | 2023-12-27 | 24 | 35 | 3 | Risk should trend down with the implementation of suite of events. | Liaise with Donald (COO) regarding Org wide strategy (competitive offers etc).
Business Disruption | Sharon Lang | Program Director | Develop draft emergency plan | 70% | On Track | 2020-11-16 | 2021-06-16 | 2024-01-16 | 31 | 38 | 1 | Risk is trending up - organisation wide. | Set up time to meet with Potential Primary Risk Owner
Business Disruption | Sharon Lang | Program Director | Implementation of alternative strategies | 35% | Off-Track | 2020-12-15 | 2021-02-14 | 2023-02-14 | 24 | 25 | 4 | Government funding is approved, anticipated in place by March 2023. | Current controls are periodically reviewed.
Change in industry conditions | Pamela Jones | Occupational Therapy Manager | Review of lease agreements | 80% | Monitor | 2020-01-30 | 2020-05-30 | 2024-12-30 | 55 | 59 | 2 | Pending funding/ability to move to a new space to reduce risk - no change. | Risk is stable - at target level.